## Project Process Tailoring Form
|  |  | Project Process Tailoring Form |  |  |  |  | PMW-PLAN-TP-06
Project ID |  |  | Tet 21 |  | Project Name | MahaTET
Last Updated On (Date) |  |  | 13 -7 2021 |  | Last updated By | Mugdha
Sr. No. | Category | Capability Area | CMMI Model Practice Area | Type | Document Name |  | Applicability | Alternate Template | Reason for Tailoring
1 | Doing | Engineering & Development Products | Product Integration (PI) | Process | EDP-PI-PR-01-Product Integration (PI)
|  |  |  | Template & Form | EDP-PI-TP-01-Release Note |  | Yes
[5 empty] | EDP-PI-TP-01-Unit Test Cases |  | Yes
2 | Doing | Engineering & Development Products | Technical Solutions (TS) | Process | EDP-TS-PR-01-Technical Solutions (TS) |  | Yes
5 |  | Engineering & Development Products | Technical Solutions (TS) | Checklist | EDP-TS-CL-01-Architecture Checklist |  | Yes
6 |  | Engineering & Development Products | Technical Solutions (TS) |  | EDP-TS-CL-02-Detailed design Checklist |  | Yes
7 |  | Engineering & Development Products | Technical Solutions (TS) | Guideline | EDP-TS-GL-01-Design Guideline |  | Yes
8 |  | Engineering & Development Products | Technical Solutions (TS) |  | EDP-TS-GL-02-Impact Analysis Guideline |  | Yes
9 |  | Engineering & Development Products | Technical Solutions (TS) | Template & Form | EDP-TS-TP-01-Architecture Document |  | Yes
10 |  | Engineering & Development Products | Technical Solutions (TS) |  | EDP-TS-TP-02-Detailed design document |  | Yes
11 |  | Engineering & Development Products | Technical Solutions (TS) |  | EDP-TS-TP-03-User Manual |  | Yes
12 |  | Engineering & Development Products | Technical Solutions (TS) |  | EDP-TS-TP-04-Impact Analysis |  | Yes
3 | Doing | Ensuring Quality | Peer Review (PR) | Process | ENQ-PR-PR-01-Peer Review (PR) |  | Yes
|  | Ensuring Quality | Peer Review (PR) | Template & Form | ENQ-PR-TP-01-Peer Review Log |  | Yes
4 | Doing | Ensuring Quality | Process Quality Assurance (PQA) | Process | ENQ-PQA-PR-01-Process Quality Assurance (PQA) |  | Yes
| Doing | Ensuring Quality | Process Quality Assurance (PQA) | Checklist | ENQ-POA-CH-01-PQA SQA Review Checklist |  | Yes
| Doing | Ensuring Quality | Process Quality Assurance (PQA) | Template & Form | ENQ-POA-TP-01-PQA Annual Audit Plan |  | Yes
| Doing | Ensuring Quality | Process Quality Assurance (PQA) |  | ENQ-POA-TP-02-PQA Audit Schedule |  | Yes
| Doing | Ensuring Quality | Process Quality Assurance (PQA) |  | ENQ-POA-TP-03-PQA Non Compliance Report |  | Yes
| Doing | Ensuring Quality | Process Quality Assurance (PQA) |  | ENQ-PQA-TP-04-PQA Audit Summary Report |  | Yes
5 | Doing | Ensuring Quality | Requirement Development & Management (RDM) | Process | ENQ-RDM-PR-01-Requirement Development & Management (RDM) |  | Yes
| Doing | Ensuring Quality | Requirement Development & Management (RDM) | Process | ENQ-RDM-TP-01-System Requirement Specification |  | Yes
| Doing | Ensuring Quality | Requirement Development & Management (RDM) | Process | ENQ-RDM-TP-02-Requirement Tracibility Matrix |  | Yes
6 | Doing | Ensuring Quality | Verification & Validation (VV) | Process | ENQ-VV-PR-01-Verification & Validation (VV) |  | Yes
| Doing | Ensuring Quality | Verification & Validation (VV) | Template & Form | ENQ-VV-TP-01-Test Plan |  | Yes
| Doing | Ensuring Quality | Verification & Validation (VV) |  | ENQ-VV-TP-02-Test Cases |  | Yes
| Doing | Ensuring Quality | Verification & Validation (VV) |  | ENQ-VV-TP-03-Defect Log |  | No | Bugzila | As we are using the same tool for past project.
7 | Managing | Managing Business Resilience | Risk & Opportunity Management (RSK) | Process | MBR-RSK-PR-01-Risk & Opportunity Management (RSK) |  | Yes
|  | Managing Business Resilience | Risk & Opportunity Management (RSK) | Guideline | MBR-RSK-GL-01-Risk & Opportunity Management (RSK) |  | Yes
|  | Managing Business Resilience | Risk & Opportunity Management (RSK) | Checklist | MBR-RSK-CH-01-Risk & Opportunity Checklist |  | Yes
|  | Managing Business Resilience | Risk & Opportunity Management (RSK) | Template & Form | MBR-RSK-TP-01-Risk & Opportunity Log |  | Yes
8 | Managing | Managing the Workfource | Organizational Training (OT) | Process | MWF-OT-PR-01-Organizational Training |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) | Template & Form | MWF-OT-TP-01-Training Plan |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-02-Training Schedule |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-03-Training Attendance Form |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-04-Training Feedback Form |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-05-Organizational Training Need |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-06-List of Trainner |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-07-Training Request Form |  | Not Applicable
| Managing | Managing the Workfource | Organizational Training (OT) |  | MWF-OT-TP-08-Training Waiver Form |  | Not Applicable
9 | Managing | Planning & Managing Work | Estimating (EST) | Process | PMW-EST-PR-01-Estimation |  | Yes
| Managing | Planning & Managing Work | Estimating (EST) | Guideline | PMW-EST-GL-01-Estimation |  | Yes
| Managing | Planning & Managing Work | Estimating (EST) | Template & Form | PMW-EST-TP-01-Estimation CBI |  | Yes
| Managing | Planning & Managing Work | Estimating (EST) |  | PMW-EST-TP-02-Estimation WBS 3 Point |  | Not Applicable
| Managing | Planning & Managing Work | Estimating (EST) |  | PMW-EST-TP-03-Estimation FP |  | Yes
10 | Managing | Planning & Managing Work | Planning (PLAN) | Process | PMW-PLAN-PR-01-Planning |  | Yes
47 |  | Planning & Managing Work | Planning (PLAN) | Template & Form | PMW-PLAN-TP-01-Project Plan |  | Yes
48 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-TP-02-Issue Tracker |  | Yes
49 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-TP-03-Action Item Tracker |  | Yes
50 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-TP-05-Lesson Learnt |  | Yes
[5 empty] | PMW-PLAN-TP-06-Project Process Tailoring |  | Yes
[5 empty] | PMW-PLAN-TP-07-Project Closure Report |  | Yes
50 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-TP-08-Project Schedule |  | Yes
51 |  | Planning & Managing Work | Planning (PLAN) | Guideline | PMW-PLAN-GL-01-Life Cycle Guideline |  | Yes
52 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-GL-02-Process Tailoring Guidelines |  | Yes
53 |  | Planning & Managing Work | Planning (PLAN) |  | PMW-PLAN-GL-03-Team Guideline and Rules |  | Yes
11 | Managing | Planning & Managing Work | Monitor & Control (MC) | Process | PMW-MC-PR-01-Monitor & Control |  | Yes
| Managing | Planning & Managing Work |  | Template & Form | PMW-MC-TP-01-Project Status Report |  | Yes
12 | Enabling | Supporting Implementation | Causal Analysis & Resolution (CAR) | Process | SI-CAR-PR-01-Causal Analysis & Resolution |  | Yes
|  |  |  | Template & Form | SI-CAR-TP-01-Causal Analysis Report |  | Yes
13 | Enabling | Supporting Implementation | Configuration Management (CM) | Process | SI-CM-PR-01-Configuration Management |  | Yes
59 | Enabling |  | Configuration Management (CM) | Template & Form | SI-CM-TP-01-Change Request Form |  | Yes
60 | Enabling |  | Configuration Management (CM) |  | SI-CM-TP-02-Change Request Tracker |  | Yes
61 | Enabling |  | Configuration Management (CM) |  | SI-CM-TP-03-Configuration Baseline Register |  | Yes
62 | Enabling |  | Configuration Management (CM) |  | SI-CM-TP-04-Configuration Audit Report |  | Yes
14 | Enabling | Supporting Implementation | Decision Analysis & Resolution (DAR) | Process | SI-DAR-PR-01-Decision Analysis & Resolution (DAR) |  | Yes
| Enabling | Supporting Implementation | Decision Analysis & Resolution (DAR) | Template & Form | SI-DAR-TP-01-Decision Analysis & Resolution |  | Yes
15 | Improving | Improving Performance | Managing Performance & Management (MPM) | Guideline | IMP-MPM-GL-01-Managing Performance & Measurement |  | Yes
66 | Improving | Improving Performance |  | Process | IMP-MPM-PR-01-Managing Performance & Measurement |  | Yes
67 | Improving | Improving Performance |  | Template & Form | IMP-MPM-TP-01-Measurement Analysis |  | Yes
16 | Improving | Improving Performance | Process Asset Development & Management Process (PAD & PCM) | Guideline | IMP-PAD-GL-01-QMS Document and Data Control |  | Not Applicable
69 | Improving | Improving Performance |  | Process | IMP-PAD-PR-01-Process Asset Development & Management Process |  | Not Applicable
70 | Improving | Improving Performance |  | Template & Form | IMP-PAD-TP-01-Process Improvement Plan |  | Not Applicable
71 | Improving | Improving Performance |  |  | IMP-PAD-TP-01-QMS Master List |  | Not Applicable
72 | Improving | Improving Performance |  |  | IMP-PAD-TP-02-Template Word New Process Definition |  | Not Applicable
73 | Improving | Improving Performance |  |  | IMP-PAD-TP-03-Template Excel |  | Not Applicable
74 | Improving | Improving Performance |  |  | IMP-PAD-TP-04-MOM |  | Not Applicable
75 | Improving | Improving Performance |  |  | IMP-PAD-TP-05-Template Word |  | Not Applicable
76 | Improving | Improving Performance |  |  | IMP-PAD-TP-06-Process Improvement Proposal Form |  | Not Applicable
77 | Improving | Improving Performance |  |  | IMP-PAD-TP-07-Process Improvement Tracker |  | Not Applicable
78 | Improving | Improving Performance |  |  | IMP-PAD-TP-08-Change Request Register |  | Not Applicable
79 | Improving | Improving Performance |  |  | IMP-PAD-TP-09-Change Request Log |  | Not Applicable