## Summary
|  | Project Estimation - Complexity based Index |  | PMW-EST-TP-01
|  |  | Estimation Iteration # | 1
Project / Proposal Name |  | MahaTET 2021 | Project / Proposal Number | TET 21
Customer / Prospect Name |  | MSCE | RFP / Spec Name and Date | 2021-06-28
Practice / Business Unit
Estimations done by |  | Mugdha | Estimates Approved By | Senior Management
Remarks |  | NA
Assumptions |  | NA
Template Revision History
Ver. No. | Release Date | Created By | Reviewed By | Approved By | Remark
0.1 | 2017-05-24 | Prasad M |  |  | Initial Draft
1 | 2021-06-15 |  | SEPG | SEPG | Approved and Baselined
Documents History
Ver. No. | Release Date | Created By | Reviewed By | Approved By | Remark
0.1 | 2021-05-24 | Mugdha | Sumit |  | First draft for stakeholder's review
1 | 2021-07-06 | Mugdha | Sumit |  | Baseline and Released

## A.Tasks Sheet
Task Sheet
|  | Pages/Screens |  |  | Services |  |  | Database Tables/ Views/Fields |  |  | Integration (Interface) |  |  | Coding Effort
| Modules | S | M | C | S | M | C | S | M | C | S | M | C
| Exam Declare | [12 empty] | 0
| Candidate Registration | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Login Page |  | 1 | [5 empty] | 1 |  |  | 1 |  | 18
| Application Form | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Payment gateway |  |  | 1 |  | 1 |  |  | 1 |  |  |  | 1 | 30
| Print Preview | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Transaction history | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Admit card paper 1 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Admit card paper 2 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| Controller Login | [12 empty] | 0
| Admin | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 14
| EO/EI Login | 1 |  |  | 1 |  |  | 1 |  |  |  | 1 |  | 18
| Centre allocation | 1 |  |  | 1 |  |  |  |  | 1 |  |  | 1 | 24
| QMS | [12 empty] | 0
| Marks Verification | 1 |  |  |  |  | 1 |  |  | 1 |  |  | 1 | 30
| Reports | 1 |  |  |  |  | 1 |  |  | 1 |  | 1 |  | 26
0
0
0
0
0
0
0
0
0
0
0
0
244
| Total | 11 | 1 | 1 | 9 | 1 | 2 | 8 | 2 | 3 | 7 | 3 | 3
| Weightages | 2 | 3 | 5 | 1 | 2 | 4 | 1 | 1 | 2 | 3 | 5 | 7
| Unadjusted CBI | 22 | 3 | 5 | 9 | 2 | 8 | 8 | 2 | 6 | 21 | 15 | 21
| Total Unadjusted CBI | 122

## B.CBI
Complexity based Index Estimation
INFLUENCE FACTORS |  | Efforts Distribution & Conversion
Data Communications |  | Elapsed Time (days working) | % Effort | Effort in Hours | Suggestive % Distribution | Elapsed time (working days)
Distributed Functions |  | Requirement Analysis | 15% | 183 | 15% | 22.875
Performance Objectives |  | Architecture Design/High Level Design | 10% | 122 | 10% | 15.25
Heavily Used Configuration |  | Detailed Design/Program Spec | 15% | 183 | 10% | 22.875
Transaction Rate |  | Coding | 40% | 488 | 40% | 61
On line Data entry |  | Unit Testing | 5% | 61 | 10% | 7.625
End-User Efficiency |  | Integration Testing | 7% | 85 | 7% | 10.625
On line Update |  | System Testing | 6% | 73 | 6% | 9.125
Complex Processing |  | User Manual /Documentation | 2% | 24 | 2% | 3
Reusability Consideration |  | Total SDLC Effort [A] | 100% | 1220 | 100%
Installation Ease |  | Project Management Effort | 7% | 85 | 7%
Operational Ease |  | Quality Assurance | 5% | 61 | 5%
Multiple Sites |  | UAT Efforts [B] | 10% | 122
Facilitate Change |  | Contingency % [C] | 10% | 122
Sum of influencing factors | 0 | Total Project Efforts (Person Hours) [A+B+C] |  | 1610
VAF =(1.00 +(.01*(Sum of Influence factors) Value Added Factors | 1 | Effort (person days) |  | 201 |  | Assuming 22*8 days/month
Total Unadjusted CB Index | 122 | Effort (person months) |  | 9.1477
Total Adjusted CB Index | 122 | Note
Productivity (Person hours/CBI) | 4 | * The elapsed time in days is Working Days and not Calender Days.
Effort Estimates (Person Hours) | 488
1220
Note on C23: (This is base productivity taken for estimation. But going forward this will keep chaning based on organizational baseline)

## Guidelines
Complexity Size Matrix (in Task Units)
Complexity | Type of Change
| Pages/Screens | Services | Database | Integration with Other Systems
Simple | 2 | 1 | 1 | 3
Medium | 3 | 2 | 1 | 5
Complex | 5 | 4 | 2 | 7
Criteria for Complexity Definitions
Complexity | Type of Change - Criteria
| Pages/Screen | Services | Database Table/Views/Fields | Integration with Other Systems
Simple | Page / Screen Consist of 5 Fields with Complete CRUD * | <=2 classes/services impacted | 1 table/View/Synonm consist of <=5 Fields | interface with simple API call or 1 messaging component
Medium | Page/Screen consists more than 5 Fields to 10 Fields with Complete CRUD * | >2 to <=5 classes/services Impacted | 1 to 3 tables/view/Synonm More than 5 Fields | multiple interfaces with simple API calls or messages
Complex | Page/Screen consists more than 10 Fields with Complete CRUD * | >5 classes/services Impacted | more than 3 tables/view/Synonm More than 5 Fields | interface with no API call definition - API to be developed
V Complex | BreakDown | Break Down | Break Down | Break Down
Note: * CRUD -> Create, Read, Update and Delete
INFLUENCE FACTORS Definition
Data communications: |  | How many communication facilities are there to aid in the transfer or exchange of information with the application or system?
Distributed data processing: |  | How are distributed data and processing functions handled?
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| #REF! | #REF!
| SimplePages/Screens | 2
| SimpleServices | 1
| SimpleDatabase | 1
| SimpleIntegration with Other Systems | 3
| MediumPages/Screens | 3
| MediumServices | 2
| MediumDatabase | 1
| MediumIntegration with Other Systems | 5
| Complex Pages/Screens | 5
| Complex Services | 4
| Complex Database | 2
| Complex Integration with Other Systems | 7
Performance: |  | Did the user require response time or throughput?
Heavily used configuration: |  | How heavily used is the current hardware platform where the application will be executed?
Transaction rate: |  | How frequently are transactions executed; daily, weekly, monthly, etc.?
On-Line data entry: |  | What percentage of the information is entered On-Line?
End-user efficiency: |  | Was the application designed for end-user efficiency?
On-Line update: |  | How many ILFs are updated by On-Line transaction?
Complex processing: |  | Does the application have extensive logical or mathematical processing?
Reusability: |  | Was the application developed to meet one or many users are needs?
Installation ease: |  | How difficult is conversion and installation?
Operational ease: |  | How effective and/or automated are start-up, back up, and recovery procedures?
Multiple sites: |  | Was the application specifically designed, developed, and supported to be installed at multiple sites for multiple organizations?
Facilitate change: |  | Was the application specifically designed, developed, and supported to facilitate change?