## Project Schedule
|  | Project Schedule |  |  |  |  | PMW-PLAN-TP-04
Project ID |  | TET 21 |  | Project Name |  | MahaTET
Last Updated On (Date) |  | 2021-07-13 |  | Last updated By |  | Mugdha
| Task Name |  | Duration | Start | Finish | Predecessors | Resources Names | Completion %
| MahaTET |  | 87 days
| Initiation and Planning |  | 2 days | 2021-07-01 | 2021-07-02
| Prepare Initial Estimates |  | 1 day | 2021-07-01 | 2021-07-01 |  | Mugdha
| Conduct Initiation Meeting |  | 1 | 2021-07-02 | 2021-07-02 |  | Mugdha
| Project Planing |  | 8 day | 2021-07-05 | 2021-07-14 |  | Mugdha
| Prepare Initial Project Schedule(MPP) |  | 1 day | 2021-07-05 | 2021-07-05 |  | Mugdha
| Prepare Project Plan |  | 3 day | 2021-07-07 | 2021-07-09 |  | Mugdha
| Configuration Management |  | 0.5 days | 2021-07-08 | 2021-07-08 |  | Ranjit
| Identification of Configuration Items |  | 0.5 days | 2021-07-08 | 2021-07-08 |  | Ranjit , Akash
| Establishment of Configuration Management Plan |  | 0.5 days | 2021-07-09 | 2021-07-09 |  | Ranjit , Akash
| Risk Management Planning |  | 2 hrs | 2021-07-12 | 2021-07-12 |  | Mugdha
| Measurement and Analysis Planning |  | 2 hrs | 2021-07-12 | 2021-07-12 |  | Mugdha
| Quality Assurance & Review Planning |  | 2 hrs | 2021-07-15 | 2021-07-15 |  | Mugdha
| Test Plan |  | 1 | 2021-07-12 | 2021-07-13 |  | Mugdha
| Preparation of Process Tailoring |  | 2 hrs | 2021-07-13 | 2021-07-13 |  | Mugdha
| Supervisory Review of Project Plan & MPP |  | 1 hrs | 2021-07-13 | 2021-07-13 |  | Mugdha
| SQA/SEPG Review of Project Plan & Tailoring |  | 1 hr | 2021-07-13 | 2021-07-13 |  | Sumit
| Revise Project Plan and/or MPP |  | 1 hr | 2021-07-13 | 2021-07-13 |  | Sumit , Mugdha
| Sign-Off Project Plan and MPP |  | 1 hr | 2021-07-13 | 2021-07-13 |  | Mugdha
| Conduct Training to Team members |  | 1 day | 2021-07-14 | 2021-07-14 |  | Mugdha
| Requirement Analysis |  | 16.5 days | 2021-07-05 | 2021-07-27
| Requirement Gathering |  | 5 days | 2021-07-05 | 2021-07-12 |  | Mugdha
| Preparation of Business Requirement Specification |  | 2 | 2021-07-13 | 2021-07-14 |  | Mugdha
| Review of Business Requirement Specification |  | 1 | 2021-07-13 | 2021-07-13 |  | Mugdha
| System Requirement Specification Document |  | 1
| Preparation of SRS |  | 2 | 2021-07-14 | 2021-07-15 |  | Mugdha
| Peer Review of SRS |  | 0.5 days | 2021-07-16 | 2021-07-16 |  | Mugdha
| Supervisory Review of SRS |  | 1 hr | 2021-07-16 | 2021-07-16 |  | Sumit
| Revision of SRS |  | 1 hr | 2021-07-16 | 2021-07-16 |  | Sumit, Mugdha
| Revision of SRS based on Client comments |  | 1 hr | 2021-07-17 | 2021-07-17 |  | Mugdha
| Preparation of RTM |  | 2 hrs | 2021-07-18 | 2021-07-18 |  | Mayuri , Ranjit
| Prepare System Test Cases (STG) |  | 11 days | 2021-08-05 | 2021-08-20 |  | Mayuri
| Revise Estimates | [5 empty] | Mugdha
| Mockup / Prototype |  | 3 days | 2021-07-20 | 2021-07-22 |  | Mugdha
| Mockup / Prototype |  | 1 day | 2021-07-21 | 2021-07-21 |  | Mugdha
| Mock-up Demostration to Client |  | 1 day | 2021-09-28 | 2021-09-29 |  | Mugdha
| Cllient Approval of Requirements |  | 1 day | 2021-07-23 | 2021-07-23 |  | Mugdha
| Project Team Meeting for understanding |  | 1 hr | 2021-07-24 | 2021-07-24 |  | Mugdha
| Configuration Management Audit |  | 0.5 days | 2021-07-26 | 2021-07-26 |  | Mugdha
| SQA Review |  | 0.5 days | 2021-07-26 | 2021-07-26 |  | Sumit
| Conduct Milestone review meeting |  | 4 hrs | 2021-08-05 | 2021-08-05 |  | Mugdha
| System Design(HLD) |  | 12.5 days | 2021-07-19 | 2021-07-30 |  | Architect
| Identify alternatives and select best alternatives using DAR |  | 4 hrs | 2021-07-19 | 2021-07-19 |  | Architect
| Preparation of Architecture |  | 5 days | 2021-07-19 | 2021-07-23 |  | Architect
| Supervisory Review of Architecture |  | 2 days | 2021-07-23 | 2021-07-24 |  | Mugdha
| Revision of Architecture (HLD) |  | 2 hrs | 2021-07-25 | 2021-07-25 |  | Architect
| Modification of RTM |  | 2 hrs | 2021-08-04 | 2021-08-04 |  | Ranjit, Akash
| Prepare Integration Test Cases (ITG) |  | 11 days | 2021-08-05 | 2021-08-20 |  | Mayuri ,
| Conduct Milestone review meeting |  | 4 hrs | 2021-08-20 | 2021-08-20 |  | Mugdha
| Detail Design(DLD) |  | 12.5 days | 2021-07-19 | 2021-07-30 |  | Architect
| Preparation of Detail Design |  | 5 days | 2021-07-24 | 2021-07-29 |  | Architect
| Review and Approval of Detail Design |  | 2 hrs | 2021-07-30 | 2021-07-30 |  | Mugdha
| Revision of Detail Design (DLD) |  | 2 hrs | 2021-07-30 | 2021-07-30 |  | Mugdha
| Prepare Unit Test Cases (UTG) |  | 3 hrs | 2021-07-30 | 2021-07-30 |  | Ranjit, Akash
| Modification of RTM |  | 2 hrs | 2021-08-04 | 2021-08-04 |  | Ranjit, Akash
| SQA Reviews/Audits |  | 1 day | 2021-08-20 | 2021-08-20
| CM Audit |  | 2 hrs |  |  |  | Mugdha
| SQA Review |  | 1 day | 2021-08-20 | 2021-08-21 |  | Sumit
| Coding & Unit Testing |  | 39.5 days |  |  |  | Mugdha
| TET announcement | [5 empty] | Mugdha
| 1.Candidate Registrattion |  | 2 days | 2021-08-04 | 2021-08-06 |  | Ranjit
| 2.Candidate Login page |  | 2 days | 2021-08-04 | 2021-08-06 |  | Akash
| 3. Application form |  | 2 days | 2021-08-04 | 2021-08-11 |  | Tahir
| 4. Payment gateway |  | 2 days | 2021-08-06 | 2021-08-10 |  | Ranjit
| 5.Print Preview |  | 2 days | 2021-08-11 | 2021-08-12 |  | Akash
| 6 Transaction History |  | 2 days | 2021-08-12 | 2021-08-13 |  | Tahir
| 7.Admit Cards 2 |  | 2 days | 2021-08-13 | 2021-08-14 |  | Akash
| Unit Test 1 | [5 empty] | Ranjit
| EO / EI login module 2 |  | 3.5
| 1. EO login page |  | 0.5 days | 2021-08-16 | 2021-08-16 |  | Ranjit
| 2. Eo profile |  | 0.5 days | 2021-08-16 | 2021-08-16 |  | Akash
| 3. EO dashboard |  | 0.5 days | 2021-08-17 | 2021-08-17 |  | Ranjit
| 4. EO center creation |  | 0.5 days | 2021-08-17 | 2021-08-17 |  | Ranjit
| 5. EO centerwise candidate allocation |  | 0.5 days | 2021-08-18 | 2021-08-18 |  | Akash
| UT of Module 2 |  | 0.5 days | 2021-08-18 | 2021-08-18 |  | Ranjit
| Admin Module |  | 3.5 |  |  |  | Mugdha
| 1. Admin Login |  | 0.5 days | 2021-08-19 | 2021-08-19 |  | Ranjit
| 2. Admin Dashboard |  | 0.5 days | 2021-08-19 | 2021-08-19 |  | Akash
| 3. EO/EI Details |  | 0.5 days | 2021-08-20 | 2021-08-20 |  | Tahir
| 4. Center Details |  | 0.5 days | 2021-08-20 | 2021-08-20 |  | Tahir
| UT of Module 3 |  | 0.5 days | 2021-08-21 | 2021-08-21 |  | Akash
| Code Review of Module N |  | 1 day | 2021-08-22 | 2021-08-22 |  | Ranjit , Akash
Modification of RTM
| Build Preparation |  | 1 day | 2021-08-31 | 2021-09-01 |  | Mugdha
| CM Audit |  | 0.5 days | 2021-07-08 | 2021-07-08 |  | Mugdha
| SQA Review |  | 0.5 days | 2021-07-08 | 2021-07-08 |  | Mugdha
| Testing |  | 22 days
| Modify IT Test cases |  | 12 days | 2021-08-20 | 2021-09-07 |  | Madhav
| Review and approval of IT test cases |  | 1 day | 2021-08-20 | 2021-08-23 |  | Mayuri
| Revise IT test cases |  | 1 day | 2021-08-23 | 2021-08-24 |  | Madhav
| Modification of RTM |  | 1 day | 2021-09-01 | 2021-09-01 |  | Mayuri
| Modify ST Test cases |  | 1 day | 2021-08-24 | 2021-08-24 |  | Mayuri
| Review and approval of ST test cases |  | 0.5 day | 2021-08-25 | 2021-08-25 |  | Mugdha
| Revise ST test cases |  | 0.5 day | 2021-08-25 | 2021-08-25 |  | Mayuri , Madhav
Modification of RTM
| Execution of Test Cases |  | 12 days |  |  |  | Mugdha
| Integration Testing |  | 1 day | 2021-08-23 | 2021-08-24 |  | Mayuri , Madhav
| Bug Resolution of Integration Testing |  | 1 day | 2021-08-24 | 2021-08-25 |  | Ranjit , Akash
| System Testing |  | 1 day | 2021-08-25 | 2021-08-25 |  | Mayuri , Madhav
| Bug Resolution of System Testing |  | 12 days | 2021-09-01 | 2021-09-17 |  | Mayuri , Madhav
| Reviews for Testing Logs |  | 2 hrs |  |  |  | Mugdha
| Modification of RTM |  | 1 day | 2021-09-01 | 2021-09-02 |  | Mugdha
| CM Audit |  | 0.5 days | 2021-07-08 | 2021-07-08 |  | Ranjit
| SQA Review |  | 0.5 days | 2021-09-21 | 2021-09-21 |  | Sumit
| User Documentation |  | 2 days | 2021-09-17 | 2021-09-21
| Preparation of Help / User Manual |  | 2 days | 2021-09-17 | 2021-09-21 |  | Mugdha
| Supervisory Review of Help / User Manual |  | 2 days | 2021-09-17 | 2021-09-17 |  | Mugdha
| Release & Deployment |  | 7.5 day | 2021-09-21 | 2021-09-30 |  | Ranjit , Akash
| Preparation of Release Note |  | 0.5 days | 2021-09-21 | 2021-09-21 |  | Ranjit , Akash
| Review and Approval of Release note |  | 0.5 days | 2021-09-22 | 2021-09-22 |  | Ranjit , Akash
| Delivery / Uploading of Code |  | 0.5 days | 2021-09-22 | 2021-09-22 |  | Ranjit , Akash
| Acceptance Testing |  | 5 day | 2021-09-23 | 2021-09-28 |  | Ranjit , Akash
| UAT Sign-off |  | 0.5 days | 2021-09-30 | 2021-09-30 |  | Ranjit , Akash
| Project Closure |  | 0.75 days |  |  |  | Mugdha
| Project Closure Meeting |  | 2 hrs | 2021-10-01 | 2021-10-01 |  | Mugdha
| Update Organization Repository |  | 0.5 days | 2021-10-01 | 2021-10-01 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) |  | 55.25 days | 2021-07-15 | 2021-09-30 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 1 |  | 2 hrs | 2021-07-15 | 2021-07-15 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 2 |  | 2 hrs | 2021-07-30 | 2021-07-30 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 3 |  | 2 hrs | 2021-08-16 | 2021-08-16 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 4 |  | 2 hrs | 2021-08-30 | 2021-08-30 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 4 |  | 2 hrs | 2021-09-15 | 2021-09-15 |  | Mugdha
| Project Progress Review(Issue, Risk Tracking) 4 |  | 2 hrs | 2021-09-30 | 2021-09-30 |  | Mugdha
| Measurement Data Collection & Analysis |  | 44.25 days | 2021-07-30 | 2021-09-30 |  | Mugdha
| Measurement Data Collection & Analysis 1 |  | 2hr | 2021-07-30 | 2021-07-30 |  | Mugdha
| Measurement Data Collection & Analysis 2 |  | 2 hrs | 2021-08-30 | 2021-08-30 |  | Mugdha
| Measurement Data Collection & Analysis 3 |  | 2 hrs | 2021-09-30 | 2021-09-30 |  | Mugdha
Senior Management Review
| Senior Management Review 1 |  | 1 hr | 2021-07-25 | 2021-07-25 |  | Sunil Pawar
| Senior Management Review 2 |  | 1 hr | 2021-08-25 | 2021-08-25 |  | Sunil Pawar
| Senior Management Review 3 |  | 1 hr | 2021-09-25 | 2021-09-25 |  | Sunil Pawar
Internal Team Meetings
| Internal Team Meetings 1 |  | 1 hr | 2021-07-13 | 2021-07-13 |  | Mugdha
| Internal Team Meetings 2 |  | 1 hr | 2021-07-24 | 2021-07-24 |  | Mugdha
| Internal Team Meetings 3 |  | 1 hr | 2021-08-07 | 2021-08-07 |  | Mugdha
| Internal Team Meetings 4 |  | 1 hr | 2021-08-14 | 2021-08-14 |  | Mugdha
| Internal Team Meetings 5 |  | 1 hr | 2021-08-28 | 2021-08-28 |  | Mugdha
| Internal Team Meetings 6 |  | 1 hr | 2021-09-11 | 2021-09-11 |  | Mugdha
| Internal Team Meetings 7 |  | 1 hr | 2021-09-25 | 2021-09-25 |  | Mugdha
| Internal Team Meetings 8 |  | 1 hr | 2021-10-09 | 2021-10-09 |  | Mugdha
| Update Organization Project Repository(PAL) |  | 0.13 days | 2021-09-30 | 2021-09-30
| Update Organization Project Repository(PAL) 1 |  | 1 hr | 2021-09-30 | 2021-09-30
| Update Organization Project Repository(PAL) 2 |  | 1 hr | 2021-09-30 | 2021-09-30