## Risk & Opportunity Checklist
|  | Risk & Opportunity Monitoring Checklist | MahaTET
Sr. No. | Risk Factor |  | Yes / No / NA | Risk & Opportunity Indicator | Guidelines
1 | Are requirements for the product stable? |  | Yes |  | NO
2 | Are requirements missing or incompletely specified? |  | No |  | YES
3 | Are requirements unclear? |  | No |  | YES
4 | Do you and the customer understand the same thing by the requirements? |  | Yes |  | NO
5 | Are requirements infeasible from an analytical point of view? |  | No |  | YES
6 | Do requirements specify something never done before, or that organization has not done before? |  | No |  | YES
7 | Are specific methods used for software analysis? |  | NA |  | NO
8 | Is there a documented statement of work? |  | Yes |  | NO
9 | Are you confident of the validity of the size estimates? |  | Yes |  | NO
10 | Are there any potential problems in meeting functionality requirements? |  | No |  | YES
11 | Will the design be difficult to achieve? |  | No |  | YES
12 | Are the internal interfaces (hardware and software) well defined and controlled? |  | Yes |  | NO
13 | Does the software interface with new or unproven hardware? |  | No |  | YES
14 | Does the software to be built interface with other software or hardware products that are unproven or new to our organization? |  | No |  | YES
15 | Are there stringent response time or throughput requirements? |  | No |  | YES
16 | Is the product difficult to test? |  | No |  | YES
17 | Are there tight constraints on the target hardware? |  | Yes | Risk | YES
18 | Do you foresee any problems reusing software not developed by you? |  | Yes | Risk | YES
19 | Do requirements for the product demand creation of a program components that are unlike any previously developed by your organization? |  | No |  | YES
20 | Is a specific method used for data design? |  | Yes |  | NO
21 | Does the customer's requirements demand the creation of new algorithms or input or output technology? |  | No |  | YES
22 | Is the implementation of the design difficult or impossible? |  | No |  | YES
23 | Are the specified level and time for unit testing adequate? |  | Yes |  | NO
24 | Are specific methods used for test case design? |  | NA |  | NO
25 | Are specific conventions for coding defined and used? |  | Yes |  | NO
26 | Has the customer given any specific coding guidelines to be used which are more stringent than the organizational guidelines? |  | No |  | YES
27 | Do requirements demand the use of new analysis, design and testing methods? |  | No |  | YES
28 | Do requirements demand the use of unconventional software development methods? |  | No |  | YES
29 | Is the integration and test environment adequate? |  | Yes |  | NO
30 | Have acceptance criteria been agreed to for all requirements? |  | NA |  | NO
31 | System integration uncoordinated, poor interface definition, or inadequate facilities? |  | No |  | YES
32 | Are there experts available to review functional and technical specifications? |  | Yes |  | NO
33 | Are there any potential problems in meeting the non-functional requirements? |  | NA |  | YES
34 | Will the implementation be difficult to understand or maintain? |  | No |  | YES
35 | Are formal technical reviews of various work products conducted regularly? |  | Yes |  | NO
36 | Are results of each formal technical review documented, including errors & resources used? |  | Yes |  | NO
37 | Is the process suited to the development model, e.g., spiral, prototyping? |  | Yes |  | NO
38 | Is the same software process used for other projects? |  | Yes |  | NO
39 | Is configuration management used to maintain consistency among system/software requirements, design, code, and test cases? |  | No | Risk | NO
40 | Are the project members experienced in use of the process? Is the process understood by all staff members? |  | No | Risk | NO
41 | Does the customer understand the software process? |  | Yes |  | NO
42 | Is there a mechanism used for controlling changes to customer requirements that impact the software? |  | No | Risk | NO
43 | Is there sufficient work station processing power, memory, or storage capacity? |  | No | Risk | NO
44 | Does the development system support all phases, activities, and functions? |  | Yes |  | NO
45 | Do you think development system is difficult to use? |  | No |  | YES
46 | Does the system suffer from software bugs, down-time, insufficient built-in back-up? |  | No |  | YES
47 | Are tools for analysis and design available? |  | No | Risk | NO
48 | Are tools used to create prototype? |  | Yes |  | NO
49 | Are tools used to support production and management of documentation? |  | Yes |  | NO
50 | Does the environment make use of a database or repository? |  | Yes |  | NO
51 | Are local experts available to answer questions about the tool? |  | Yes |  | NO
52 | Are the roles and reporting relationships clear? |  | Yes |  | NO
53 | Are resources experienced in software development, software management, the application domain, the development process, or on large projects? |  | Yes |  | NO
54 | Is there poor interface with customer, other contractors, senior and/or peer managers? |  | No |  | YES
55 | Are there adequate procedures and resources to assure product quality? |  | Yes |  | NO
56 | Are configuration management tools used to control and track change activity throughout the software process? |  | Yes |  | NO
57 | Are all metrics (product quality, process quality) collected for the project? |  | Yes |  | NO
58 | Is there poor awareness of mission or goals, poor communication of technical information among peers and managers? |  | No |  | YES
59 | Is there a non-productive, non-creative atmosphere? Do people feel that there is no recognition or reward for superior work? |  | NA |  | YES
60 | Is the technology to be built new to the organization? |  | No |  | YES
61 | Is the delivery deadline unreasonable or the schedule inadequate? |  | No |  | YES
62 | Is the staff inexperienced, lacking domain knowledge, lacking skills, or understaffed? |  | No |  | YES
63 | Will all project staff be working full time on this project? |  | Yes |  | NO
64 | Will turnover among staff be low enough to allow continuity? |  | Yes |  | NO
65 | Are enough people available? |  | Yes |  | NO
66 | Does staff have the right expectations about the job at hand? |  | Yes |  | NO
67 | Has staff received necessary software training? |  | Yes |  | NO
68 | Are the facilities adequate for building and delivering the product? |  | Yes |  | NO
69 | Is the contract type a source of risk to the project? |  | NA |  | YES
70 | Does the contract cause any restrictions? |  | NA |  | YES
71 | Does the project have any dependencies on outside products or services? |  | Yes | Risk | YES
72 | Will the customer agree to spend time in formal requirements gathering meetings, reviews etc..? |  | NA |  | NO
73 | Are there any customer problems such as: lengthy document-approval cycle, poor communication, and inadequate domain expertise? |  | No |  | YES
74 | Is the customer technically sophisticated in the product area? |  | Yes |  | NO
75 | Is the customer willing to establish rapid communication with the developer? |  | Yes |  | NO
76 | Is the customer willing to let your people do their job? |  | Yes |  | NO
77 | Are there any problems with associate contractors such as inadequately defined or unstable interfaces, poor communication, or lack of cooperation? |  | No |  | YES
78 | Is the project dependent on subcontractors for any critical areas? |  | No |  | YES
79 | Is there a lack of support from senior management? |  | No |  | YES
80 | Are there a large number of end-users? |  | Yes | Risk | YES
81 | Is extensive product documentation required to be delivered to customer? |  | No |  | YES
82 | Is it difficult to deliver documentation in desired format? E.g. context sensitive online help. |  | No |  | YES
83 | Does this project has critical impact on company revenue? |  | Yes | Risk | YES
84 | Are there penalties associated with late delivery? |  | Yes | Risk | YES
85 | Are there costs associated with a defective product? |  | Yes | Risk | YES
86 | Are there Governmental constraints / statutory requirements on the construction of this product? |  | Yes | Risk | YES
87 | Is there a System performance expectation clause in the contract? E.g.. Transactions should not take more than 2 seconds? |  | NA |  | YES
88 | Is there an interface application whose functionality is not tested and proven? |  | Yes | Risk | YES
89 | Do you envisage any interface issues with 3rd party application? |  | Yes | Risk | YES
90 | Is the work environment for the project sufficiently available? |  | Yes |  | NO
91 | Is customer clear about the scope? |  | Yes |  | NO
92 | Is customer new to IT? |  | No |  | YES
93 | Is customer new to Project execution methodology? |  | No |  | YES
94 | Has any undocumented commitments given to customer during presales/marketing? |  | NA |  | YES
95 | Do you envisage any customer initiated scope creep? |  | No |  | YES
96 | Is migration of old data whose format is Unknown part of scope? |  | No |  | YES
97 | Is the project NOT present as priority item in the customer's agenda (I.e. is customer likely to deprioritize the project if he has some other issue cropping up in his regular business?)? |  | No |  | YES
98 | Is the customer clear with the kind of responsibilities from his end towards each phase of SDLC chosen? (Such as assigning a Project manager from customer end, identifying the users to attend product training and making sure that they attend etc.) |  | Yes |  | NO
99 | Any delay is expected from the Client on providing critical data which might affect the project progress? |  | Yes | Risk | YES
100 | Do you expect delays from Customer feedback on critical issues / closure of issues / clarifications? |  | Yes | Risk | YES
101 | Customer's understanding on the Design Architecture is clear? |  | Yes |  | NO