## Risk & Opportunity Log
|  |  | Risk & Opportunity Monitoring Log | [12 empty] | MBR-RSK-TP-01
Project ID |  | TET 21 | [5 empty] | Project Name |  |  | MahaTET |  |  |  | Project Type
Sr. No. | Risk Description | Source | Risk ( R ) / Opportunities (O) | Risk Evaluation (√) put a tick mark |  | Category | Risk Handling Strategy | Impact (1 to 3) | Probability (1 to 5) | Risk Factor | Severity | Mitigation Action | Contingency Action | Risk Raised Date | Expected Close Date | Actual Close Date | Status
|  |  |  | Acceptable | Unacceptable
1 | Due to Unavailability of the configuration setting we can not able to keep the document on the repository. | Resource | Risk | Accept |  | Technical | Accept | 1 | 1 | 1 | Low | Project Manager | Get the resource available for the configuration setting | 2021-07-07 | 2021-07-13 |  | Open
2
3
4
5
6
7

## Guideline
Sources | Phase | Priority | Probability | Impact | Status | Risk Type
Uncertain requirements | Planning | High | Low- ( 0- 30%) | 5-High | Closed | Financial
Inadequate staffing and skills | Analysis | Medium | Medium-(31-70%) | 3-Medium | Open | Resource
Unrealistic schedule estimates or allocation | Requirments Gathering | Low | High(>70%) | 1-Low |  | Legal
Non- availability of Critical Resource | Design |  |  |  |  | Technology
Inadequate communication with actual or potential customers or with their representatives | Coding and Unit Testing |  |  |  |  | Business
Disruptions to continuity of operations | Testing |  |  |  |  | Contract
Infeasible design | Delivery
Lack of Knowledge | project closure
Unprecedented efforts—estimates unavailable | project Management
Unavailable Technology
Cost or funding issues